## WELCOME
Overview
This tracker is designed to simplify, streamline, and standardize your daily life.
How To
1) Add your clients to the "EDIT clients" worksheet
2) Add your projects to the "EDIT projects" worksheet
3) Add your tasks to the "DO" worksheet
Key Features
Sleep easy knowing you'll never forget again
Data-driven daily completion and stretch goals
Data-driven estimated time to completion per task
Quantifiable proof that you help out around the house
Rapid, distributable by-project and client project status
Instantly available, monthly view of by client, by project effort allocation
The ability to finally answer the question, "What have I been doing with my life"

## DO
Client | Project | Category | Task | Effort | Added On | Started On | Completed On | ETC | Dependency | Status | daynum_AddedOn | daynum_StartedOn | daynum_CompletedOn | DaysInBacklog | DaysInProgress | Client_Project | Notes
Personal | ToDo | Admin | Retroactively classify task subcategories | 1 | 2018-11-19 | 2019-01-02 08:58 | 2019-01-04 |  |  | Complete | 2 | 4 | 6 | 33 | 3 | Personal_ToDo
Personal | ToDo | Admin | Ensure all todo items from Tasks_2 are brought over | 1 | 2019-06-12 | 2019-06-13 | 2019-06-13 |  |  | Complete | 4 | 5 | 5 | 2 | 1 | Personal_ToDo
Personal | ToDo | Admin | Send to Louay and Marvin and Aliya and Matt | 2 | 2019-07-17 | 2019-12-20 | 2019-12-20 |  |  | Complete | 4 | 6 | 6 | 113 | 1 | Personal_ToDo
Personal | ToDo | Admin | Clean dataDashboard_2 and bring in improved user-selectable timerange system from dynamicfilterableheatmap ws | 2 | 2019-08-15 | 2019-08-15 | 2019-08-15 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Admin | Clean up worksheets | 1 | 2019-08-15 | 2019-08-15 | 2019-08-15 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Admin | Fix ETC to handle Home, Mary, and T-Mobile tasks | 2 | 2019-08-19 | 2019-08-24 | 2019-08-24 |  |  | Complete | 2 | 7 | 7 | 5 | 1 | Personal_ToDo
Personal | ToDo | Admin | Bring over all tasks from old task tracker | 5 | 2019-08-24 | 2019-08-24 | 2019-08-25 |  |  | Complete | 7 | 7 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Admin | Avg. Started on for carried over tasks by avg. time in progress per client - the completion date listed, and put effort as 1 for all tasks | 3 | 2019-08-24 | 2019-08-24 | 2019-08-24 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Admin | Clean and consolidate all duplicate or erroneous project names. | 4 | 2019-08-24 | 2019-08-25 | 2019-08-25 |  |  | Complete | 7 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Bugs | Alter DaysinBacklog and DaysinProgress calculations to count 0 days as 1 day | 2 | 2019-07-05 | 2019-07-05 | 2019-07-05 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Data | Fix calculation considerations for overview graphs | 2 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Data | Solve for partial month averages | 2 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Discovery | Determine better system to count when tasks here were open or closed | 1 | 2018-11-05 | 2018-11-14 08:58 | 2018-11-16 |  |  | Complete | 2 | 4 | 6 | 8 | 3 | Personal_ToDo
Personal | ToDo | Discovery | Consider adding subcategory like feature, lesson learned, tech debt, need to have, etc. | 1 | 2018-11-05 | 2018-11-18 08:58 | 2018-11-20 |  |  | Complete | 2 | 1 | 3 | 10 | 2 | Personal_ToDo
Personal | ToDo | Discovery | Determine main subcategory classifications | 1 | 2018-11-19 | 2018-11-19 | 2018-11-20 |  |  | Complete | 2 | 2 | 3 | 1 | 2 | Personal_ToDo | Main classifications could be: - Discovery (Set Up) - Feature (New Ability) - Enhancement (Improves existing ability) - Fix (Restores broken functionality) - Comm (Communication Point) - Research (New Skills) - Task (General)
Personal | ToDo | Discovery | What would the benefit of subcategory classifications be? | 1 | 2018-11-19 | 2018-11-19 | 2018-11-20 |  |  | Complete | 2 | 2 | 3 | 1 | 2 | Personal_ToDo | Benefit would be quickly seeing all features, bugs, etc across projects. Tracking these items could be useful to know where time is going per project, and in quickly recapping what items have been implemented per project.
Personal | ToDo | Discovery | Research radar charts - Useful for determining what current focus is on, what is going well, or what has the most impact. | 1 | 2019-01-01 | 2019-01-04 08:58 | 2019-01-06 |  |  | Complete | 3 | 6 | 1 | 4 | 1 | Personal_ToDo
Personal | ToDo | Documentation | Document all projects purpose and utilization. | 4 | 2019-08-24 | 2019-08-24 | 2019-08-25 |  |  | Complete | 7 | 7 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Documentation | Create How To | 2 | 2019-12-20 | 2019-12-20 | 2019-12-20 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Autogenerate Date Added based on when text gets entered into the task | 1 | 2018-03-05 | 2018-03-12 08:58 | 2018-03-14 |  |  | Complete | 2 | 2 | 4 | 6 | 3 | Personal_ToDo
Personal | ToDo | Features | Find a way to take notes based on pre-defined tags for easy access, slicing, and generalization (from who: when: regarding what: etc | 1 | 2018-05-21 | 2018-07-07 08:58 | 2018-07-09 |  |  | Complete | 2 | 7 | 2 | 35 | 1 | Personal_ToDo | Can do this within OneNote via custom tags, would need to decide what tags you would want to apply. Could also do this with Excel but text notes would be difficult.
Personal | ToDo | Features | Create standardized method of tracking all project progress | 1 | 2018-07-03 | 2018-07-07 08:58 | 2018-07-09 |  |  | Complete | 3 | 7 | 2 | 4 | 1 | Personal_ToDo | Notes, Capabilities, Requests, Date input, date complete, etc
Personal | ToDo | Features | Need automatic way to move things through open items and done items per project to remove need for notepad | 1 | 2018-10-26 | 2018-11-18 08:58 | 2018-11-20 |  |  | Complete | 6 | 1 | 3 | 16 | 2 | Personal_ToDo | New process labeling project enables quickly filtering things down this way
Personal | ToDo | Features | Add to current measurement system | 1 | 2018-11-05 | 2018-11-14 08:58 | 2018-11-16 |  |  | Complete | 2 | 4 | 6 | 8 | 3 | Personal_ToDo
Personal | ToDo | Features | Create a timeline by project view showing when tasks are started, completed, opened, and blocks | 1 | 2018-11-05 | 2018-11-14 08:58 | 2018-11-16 |  |  | Complete | 2 | 4 | 6 | 8 | 3 | Personal_ToDo
Personal | ToDo | Features | Add graph showing progress per project (items complete --> items open) | 1 | 2018-11-08 | 2018-11-14 08:58 | 2018-11-16 |  |  | Complete | 5 | 4 | 6 | 5 | 3 | Personal_ToDo
Personal | ToDo | Features | Create additional graphs to gain insights on to do list | 1 | 2018-11-19 | 2018-11-19 | 2018-11-19 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Create estimated time to completion metric for fast reference when adding tasks | 1 | 2018-11-19 | 2018-11-19 | 2018-11-19 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Project level view breakout | 1 | 2018-12-12 | 2019-01-03 08:58 | 2019-01-05 |  |  | Complete | 4 | 5 | 7 | 17 | 2 | Personal_ToDo | Number of days in each state (completing items, completing items with blocks, items in queue, completely blocked) Day started, day end Number of active days # of other projects and tasks running during the same timeframe 12/13: Created starting data tables
Personal | ToDo | Features | Make a mood log. Mood, reasoning, potential related factors. Data only for this pass. | 1 | 2019-01-01 | 2019-01-01 | 2019-01-01 |  |  | Complete | 3 | 3 | 3 | 1 | 1 | Personal_ToDo | Track every day, use reminders.
Personal | ToDo | Features | Create a calendar heatmap | 1 | 2019-01-01 | 2019-01-02 08:58 | 2019-01-04 |  |  | Complete | 3 | 4 | 6 | 2 | 3 | Personal_ToDo
Personal | ToDo | Features | Input questions each graph answers above the graph | 1 | 2019-01-02 | 2019-01-04 08:58 | 2019-01-06 |  |  | Complete | 4 | 6 | 1 | 3 | 1 | Personal_ToDo
Personal | ToDo | Features | Create est completion date for project | 1 | 2019-01-05 | 2019-01-05 | 2019-01-05 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Add treemap to show what is taking the most effort | 1 | 2019-01-06 | 2019-01-06 | 2019-01-06 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Lock visuals so they don’t move on mobile if possible How: Protect sheet, select all, deselect "Edit Objects" and "Select Unlocked Cells" (to enable dv). | 1 | 2019-01-06 | 2019-01-06 | 2019-01-07 |  |  | Complete | 1 | 1 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Create monthly and weekly comparison | 1 | 2019-04-17 | 2019-04-17 | 2019-04-17 |  |  | Complete | 4 | 4 | 4 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Project list and status | 2 | 2019-05-28 | 2019-05-28 | 2019-05-28 |  |  | Complete | 3 | 3 | 3 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | ETC Calulcation which takes into account - Client Average Time In Backlog + Average Time to Complete - Complexity - Current # of Open Tasks - Items without dates removed from calculation | 3 | 2019-05-28 | 2019-07-05 | 2019-07-05 |  |  | Complete | 3 | 6 | 6 | 29 | 1 | Personal_ToDo
Personal | ToDo | Features | Project dashboard | 3 | 2019-05-28 | 2019-08-01 | 2019-08-03 |  |  | Complete | 3 | 5 | 7 | 48 | 2 | Personal_ToDo
Personal | ToDo | Features | Add key events tracker | 2 | 2019-06-09 | 2019-06-09 | 2019-06-09 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Add key dates tracker | 1 | 2019-06-12 | 2019-06-12 | 2019-07-05 |  |  | Complete | 4 | 4 | 6 | 1 | 18 | Personal_ToDo
Personal | ToDo | Features | Recurring Responsibilites Tab | 1 | 2019-06-12 | 2019-06-12 | 2019-07-05 |  |  | Complete | 4 | 4 | 6 | 1 | 18 | Personal_ToDo
Personal | ToDo | Features | Goal tracker for things like books, pushups, etc | 1 | 2019-06-25 | 2019-06-27 | 2019-06-27 |  |  | Complete | 3 | 5 | 5 | 3 | 1 | Personal_ToDo
Personal | ToDo | Features | Habits reminder | 1 | 2019-06-27 | 2019-06-27 | 2019-06-27 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Method of dynamically choosing timeframe and interval period | 4 | 2019-06-29 | 2019-06-29 | 2019-06-29 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Automatic interval x axis updates when shifting between interval options | 2 | 2019-06-29 | 2019-06-29 | 2019-06-29 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Add Days in Backlog and Days in Progress calculations | 2 | 2019-07-04 | 2019-07-04 | 2019-07-04 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Automatically enable "Overview" calculations when looking at the tab, disable when not viewing. | 3 | 2019-07-10 | 2019-07-13 | 2019-07-13 |  |  | Complete | 4 | 7 | 7 | 3 | 1 | Personal_ToDo
Personal | ToDo | Features | Project constrainer and information Status Start date, end date Last task complete date Total tasks completed, dates Implemented or not Lessons learned List of work done | 5 | 2019-07-24 | 2019-08-24 | 2019-08-24 |  |  | Complete | 4 | 7 | 7 | 23 | 1 | Personal_ToDo | 8/24/19: Project table designed and implemented. All project information needs to be filled out.
Personal | ToDo | Features | Create macro to auto-hide table rows with 0 values any time view filters are changed | 3 | 2019-08-15 | 2019-08-15 | 2019-08-24 |  |  | Complete | 5 | 5 | 7 | 1 | 7 | Personal_ToDo
Personal | ToDo | Features | Method to show value of projects over time | 2 | 2019-08-16 | 2019-08-24 | 2019-08-24 |  |  | Complete | 6 | 7 | 7 | 6 | 1 | Personal_ToDo
Personal | ToDo | Features | Create client table that this table pulls client options from. Include in the table total count per client open vs. completed, first date vs. last. Also include instructions for when adding a new client (for instance, add to x,y,z charts and the ETC calculation) | 3 | 2019-08-20 | 2019-08-24 | 2019-08-24 |  |  | Complete | 3 | 7 | 7 | 4 | 1 | Personal_ToDo | 8/24/19: Client table designed and implemented, ETC calculation subsumed into client table so update per new clients is now automatic.
Personal | ToDo | Features | Enable work usefulness graph to account for project utilization. | 2 | 2019-09-17 | 2019-09-17 | 2019-09-17 |  |  | Complete | 3 | 3 | 3 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Create a dynamically filtered table that shows all clients/projects/tasks selected | 3 | 2019-09-17 | 2019-09-17 | 2019-09-19 |  |  | Complete | 3 | 3 | 5 | 1 | 3 | Personal_ToDo | 9/17/19: https://trumpexcel.com/dynamic-excel-filter/
Personal | ToDo | Features | Create Learning table | 1 | 2019-10-07 | 2019-10-07 | 2019-10-07 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Add # of times project was "completed" and then more tasks were added. | 5 | 2019-10-18 | 2019-11-29 | 2019-11-30 |  |  | Complete | 6 | 6 | 7 | 31 | 1 | Personal_ToDo | 11/30/19: Ended up being fairly complex but still only took a few hours. Required a sorting algorithm, date modification, date extrapolation between start and end points, date checking across dates to find noncontiguous points, etc. Also, not extremely fast and erroring somehow so I need to fix that.
Personal | ToDo | Features | Add Study Resources ws and populate | 3 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Add Study Tools ws and populate | 3 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Add Study Terms ws and populate | 3 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Add Processes ws and populate | 3 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Features | Resize all rows on Gantt Project open | 2 | 2019-12-10 | 2019-12-15 | 2019-12-15 |  |  | Complete | 3 | 1 | 1 | 4 | 1 | Personal_ToDo
Personal | ToDo | Features | Create handling for when more tasks than are needed are completed | 2 | 2019-12-19 | 2019-12-20 | 2019-12-20 |  |  | Complete | 5 | 6 | 6 | 2 | 1 | Personal_ToDo
Personal | ToDo | Features | Create handling for when more tasks are projected than are in the backlog. | 2 | 2019-12-19 | 2019-12-20 | 2019-12-20 |  |  | Complete | 5 | 6 | 6 | 2 | 1 | Personal_ToDo
Personal | ToDo | Fixes | Fix border of table so it copies down correctly with each new cell | 1 | 2018-03-20 | 2018-07-07 08:58 | 2018-07-09 |  |  | Complete | 3 | 7 | 2 | 79 | 1 | Personal_ToDo | Doesn't appear to be possible, it's caused by Excel having to choose which cell gets the border. Online advice is to convert the table to a range and then back to a table, or format the headers the way you want new rows to be formatted.
Personal | ToDo | Fixes | Fix Gantt impediment count | 1 | 2018-11-28 | 2018-11-28 | 2018-11-28 |  |  | Complete | 4 | 4 | 4 | 1 | 1 | Personal_ToDo | Improved readability. Changed impediment col to always show impediment. Changed impediment countif to count if date completed is > rather than < today.
Personal | ToDo | Fixes | Fix count of in progress, currently shows blank when it should show numbers in Gantt chart | 1 | 2018-12-05 | 2018-12-08 08:58 | 2018-12-10 |  |  | Complete | 4 | 7 | 2 | 3 | 1 | Personal_ToDo
Personal | ToDo | Fixes | Fix by category views to not start from 0 | 1 | 2019-01-01 | 2019-01-02 08:58 | 2019-01-04 |  |  | Complete | 3 | 4 | 6 | 2 | 3 | Personal_ToDo
Personal | ToDo | Fixes | Fix week identifier | 1 | 2019-01-02 | 2019-01-02 | 2019-01-02 |  |  | Complete | 4 | 4 | 4 | 1 | 1 | Personal_ToDo
Personal | ToDo | Fixes | Fix weeks elapsed | 1 | 2019-01-06 | 2019-01-06 | 2019-01-06 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Fixes | Fix table border pasting white when using email | 1 | 2019-08-21 | 2019-08-21 | 2019-08-21 |  |  | Complete | 4 | 4 | 4 | 1 | 1 | Personal_ToDo | 8/21/19: Created custom table format, whole table, format, all table borders and black.
Personal | ToDo | Fixes | Fix selected work vs. other work to maintain total | 1 | 2019-09-17 | 2019-09-17 | 2019-09-17 |  |  | Complete | 3 | 3 | 3 | 1 | 1 | Personal_ToDo
Personal | ToDo | Fixes | Change task daily averages to account for ordering. | 1 | 2019-09-17 | 2019-09-17 | 2019-09-17 |  |  | Complete | 3 | 3 | 3 | 1 | 1 | Personal_ToDo
Personal | ToDo | Fixes | Fix circular reference error - fixed by going to formulas --> error checking --> found the cell and fixed the formula. | 1 | 2019-12-04 | 2019-12-06 | 2019-12-06 |  |  | Complete | 4 | 6 | 6 | 3 | 1 | Personal_ToDo
Personal | ToDo | Fixes | Fix tbClient calculations | 2 | 2019-12-20 | 2019-12-20 | 2019-12-20 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Goal | Overview of current status and workload | 3 | 2019-06-27 | 2019-06-29 | 2019-07-05 |  |  | Complete | 5 | 7 | 6 | 2 | 5 | Personal_ToDo
Personal | ToDo | QA | Double check static open items count | 2 | 2019-09-26 | 2019-10-06 | 2019-10-06 |  |  | Complete | 5 | 1 | 1 | 7 | 1 | Personal_ToDo
Personal | ToDo | QA | Ensure ETC is still correct when project has no completed items to date | 2 | 2019-09-27 | 2019-10-05 | 2019-10-05 |  |  | Complete | 6 | 7 | 7 | 6 | 1 | Personal_ToDo
Personal | ToDo | QA | Ensure ETC is correct | 2 | 2019-12-20 | 2019-12-20 | 2019-12-20 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | QA | Ensure VIEW Project right-most visual is correct | 2 | 2019-12-20 | 2019-12-20 | 2019-12-20 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Disable screen updating on macro run | 1 | 2019-07-02 | 2019-07-02 | 2019-07-02 |  |  | Complete | 3 | 3 | 3 | 1 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Restructure dynamic date range into cohesive, understandable, and replicable structure | 2 | 2019-07-27 | 2019-07-27 | 2019-07-27 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Speed up workbook | 3 | 2019-09-03 | 2019-12-01 | 2019-12-02 |  |  | Complete | 3 | 1 | 2 | 64 | 1 | Personal_ToDo | 12/2/2019: Sped up by turning off automatic calculations when this sheet is activated, and reversing this if the sheet is deactivated. Since this sheet still needs some calculations, I renabled it if target cells are used followed by immediate deactivation.
Personal | ToDo | Refactoring | Rebuild Task Manager | 3 | 2019-12-15 | 2019-12-15 | 2019-12-15 |  |  | Complete | 1 | 1 | 1 | 1 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Bring project tracker over to ADVANCE wb | 3 | 2019-12-19 | 2019-12-19 | 2019-12-19 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Bring gantt view over to ADVANCE wb | 3 | 2019-12-19 | 2019-12-19 | 2019-12-19 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Bring in all needed modules | 2 | 2019-12-19 | 2019-12-19 | 2019-12-19 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Split all previous wb worksheets into separate files based on their category | 2 | 2019-12-19 | 2019-12-20 | 2019-12-20 |  |  | Complete | 5 | 6 | 6 | 2 | 1 | Personal_ToDo
Personal | ToDo | Refactoring | Place category definitions in categories ws rather than in the formulas | 2 | 2019-12-20 | 2019-12-20 | 2019-12-20 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Updates | Update Designer with all accomplishments | 1 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  | Complete | 3 | 3 | 3 | 1 | 1 | Personal_ToDo
Personal | ToDo | Updates | Add awake/sleep times instead of hour log for increased accuracy | 1 | 2019-01-04 | 2019-01-04 | 2019-01-04 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Upkeep | Consolidate all previous ToDos | 1 | 2018-03-02 | 2018-03-04 08:58 | 2018-03-06 |  |  | Complete | 6 | 1 | 3 | 1 | 2 | Personal_ToDo
Personal | ToDo | Upkeep | Update designer | 1 | 2018-07-02 | 2018-07-02 | 2018-07-02 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Upkeep | Standardize colors across visuals | 1 | 2019-01-02 | 2019-01-03 08:58 | 2019-01-05 |  |  | Complete | 4 | 5 | 7 | 2 | 2 | Personal_ToDo
Personal | ToDo | Upkeep | Standardize column formatting on main todo list | 1 | 2019-01-04 | 2019-01-04 | 2019-01-04 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph showing avg. tasks opened vs. completed per day | 2 | 2019-06-04 | 2019-07-04 | 2019-07-04 |  |  | Complete | 3 | 5 | 5 | 23 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for count by status over time | 2 | 2019-06-29 | 2019-06-29 | 2019-06-29 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for count by status overall | 2 | 2019-06-29 | 2019-06-29 | 2019-06-29 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for cumulative complete over time | 2 | 2019-06-29 | 2019-06-29 | 2019-06-29 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for cumulative added over time | 2 | 2019-06-29 | 2019-06-29 | 2019-06-29 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for what clients are consuming the most time | 2 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Callout for selected timeframe | 1 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  | Complete | 2 | 2 | 2 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for average completion by client over time | 2 | 2019-07-04 | 2019-07-04 | 2019-07-04 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for average time in backlog across clients | 3 | 2019-07-04 | 2019-07-04 | 2019-07-04 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for total completed across clients | 2 | 2019-07-04 | 2019-07-04 | 2019-07-04 |  |  | Complete | 5 | 5 | 5 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for average time in backlog by client over time | 3 | 2019-07-04 | 2019-07-05 | 2019-07-05 |  |  | Complete | 5 | 6 | 6 | 2 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for average time in backlog | 3 | 2019-07-04 | 2019-07-05 | 2019-07-05 |  |  | Complete | 5 | 6 | 6 | 2 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Organize visuals | 2 | 2019-07-05 | 2019-07-05 | 2019-07-05 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Clean up conditional formatting on dashboard and task tab | 2 | 2019-07-05 | 2019-07-05 | 2019-07-05 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for average time in progress across clients | 2 | 2019-07-05 | 2019-07-05 | 2019-07-05 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for average time in progress over time | 2 | 2019-07-05 | 2019-07-05 | 2019-07-05 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Graph for average time in progress across time by client | 2 | 2019-07-05 | 2019-07-05 | 2019-07-05 |  |  | Complete | 6 | 6 | 6 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Backlog count over time | 2 | 2019-07-24 | 2019-08-15 | 2019-08-15 |  |  | Complete | 4 | 5 | 5 | 17 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Time and filter dynamic completion heatmap | 3 | 2019-07-27 | 2019-07-27 | 2019-07-27 |  |  | Complete | 7 | 7 | 7 | 1 | 1 | Personal_ToDo
Personal | ToDo | Visualization | Amount of work visualizer based on task * effort | 2 | 2019-09-18 | 2019-09-18 | 2019-09-18 |  |  | Complete | 4 | 4 | 4 | 1 | 1 | Personal_ToDo | 9/18/19: Completed, but it doesn't tell a different or more compelling story than the current dashboard so I'm leaving that as it is.
0-0 Remaining Tasks Today
0-1 Remaining Effort
0 Backlog Tasks
TASK MANAGER

## EDIT clients
Clients | Earliest Task | Most Recent Completion | Project Count | Task Count | Avg. Task Days in Backlog | Avg. Task Days in Progress | Avg. Task Days Total | Task Usefulness Rate
Personal | 2018-03-04 08:58 | 2019-12-20 | 1 | 114 | 6.3158 | 1.614 | 7.9298 | 100%
Formulas:
Earliest Task = MINIFS(tbTasks[Started On],tbTasks[Client],tbClients[[#This Row],[Clients]])
Most Recent Completion = MAXIFS(tbTasks[Completed On],tbTasks[Client],tbClients[[#This Row],[Clients]])

## EDIT projects
Client | Project | Purpose | Feature Highlights | Related Tools | Audience | Limitations | Future Updates | Utilized | New Methods | Lessons Learned | Notes | Owner | Tasks In Backlog | Tasks In Progress | Tasks Completed | Total Tasks | Progress | Status | First Task Added On | First Task Started On | Last Task Completed On | Client_Project | Link
Personal | ToDo | Enable superior tracking of all tasks, projects, and clients minimal continuous effort. | Sleep easy knowing you'll never forget again Data-driven daily completion and stretch goals Data-driven estimated time to completion per task Quantifiable proof that you help out around the house Rapid, distributable by-project and client project status Instantly available, monthly view of by client, by project effort allocation The ability to finally answer the question, "What have I been doing with my life" | Excel, VBA | Steven Buri |  | Exploratory analysis on correlations affecting productivity. For ex: - # of open tasks effect on # of tasks completed - task difficulty effect on task completion etc Calendar handling with reminders and heat map | Yes | - Custom live-filtering via typing feature for dashboard - By-project gantt chart - Estimated time to completion dates auto-generated based on historical completion rates per category |  |  |  | 0 | 0 | 114 | 114 | 100% | Complete | 2018-03-02 | 2018-03-04 08:58 | 2019-12-20 | Personal_ToDo | -
Formulas:
First Task Added On = IF(MINIFS(tbTasks[Added On],tbTasks[Project],tbProjects[[#This Row],[Project]])=0,"",MINIFS(tbTasks[Added On],tbTasks[Project],tbProjects[[#This Row],[Project]]))
First Task Started On = IF(MINIFS(tbTasks[Started On],tbTasks[Project],tbProjects[[#This Row],[Project]])=0,"",MINIFS(tbTasks[Started On],tbTasks[Project],tbProjects[[#This Row],[Project]]))
Last Task Completed On = IF(MAXIFS(tbTasks[Completed On],tbTasks[Project],tbProjects[[#This Row],[Project]])=0,"",MAXIFS(tbTasks[Completed On],tbTasks[Project],tbProjects[[#This Row],[Project]]))

## EDIT categories
Category | Classification | Description
Access | Potential Value Add
Admin | Potential Value Add
Analysis | Value Add
Bugs | Value Add
Comm | Non-Value Add
Core | Value Add
Data | Value Add
Design | Value Add
Discovery | Non-Value Add
Documentation | Value Add
Features | Value Add
Fixes | Value Add
Goal | Value Add
Impediment | Non-Value Add
Maintenance | Potential Value Add
Meeting | Non-Value Add
Milestone | Value Add
Practice | Value Add
Prepare | Non-Value Add
QA | Value Add
Refactoring | Value Add
Research | Value Add
Revise | Value Add
Setup | Non-Value Add
Study | Value Add
Testing | Value Add
Training | Non-Value Add
Updates | Value Add
Upkeep | Non-Value Add
Visualization | Value Add

## VIEW Project
Project View | Client | Project | From Date | To Date | Number of Completions
|  | ToDo |  |  | 4
100% Complete
Purpose Enable superior tracking of all tasks, projects, and clients minimal continuous effort.
Project Dates
3/4/2018
12/20/2019

## VIEW Gantt
By Project By Month Completion Gantt Visual | Client | Project | Progress | 2018-12-31 | 2019-01-31 | 2019-02-28 | 2019-03-31 | 2019-04-30 | 2019-05-31 | 2019-06-30 | 2019-07-31 | 2019-08-31 | 2019-09-30 | 2019-10-31 | 2019-11-30 | 2019-12-31
Personal_ToDo | Personal | ToDo | 100% |  | 15 | 0 | 0 | 1 | 1 | 10 | 25 | 14 | 5 | 3 | 1 | 20
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on E1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Left blank to account for formula needing > and < dates. Full year available to the right.

## Documentation (hidden)
Version: | 5

## metricsDO (hidden)
Goal | Count | Daily Completion Goals | Quantity | Text | Notes | Backlog Metrics | Count | Text | Task Completion | Count
Clear Backlog in X Days | 30 | First Task | 2018-03-02 |  |  | Backlog Tasks | 0 | 0 Backlog Tasks | 2019-12-27 | 0
|  | Last Task | 2019-12-20 |  |  | Started Tasks | 0 |  | 2019-12-26 | 0
|  | Total # Of Days Used | 658 |  |  | Backlog Effort | 0 |  | 2019-12-25 | 0
|  | Tasks Completed (All Time) | 114 |  |  | Started Effort | 0 |  | 2019-12-24 | 0
|  | Avg. Completion (All Time) | 0.17325 |  |  | New Tasks (Last 30 Days) | 18 |  | 2019-12-23 | 0
|  | Tasks Completed (Last 7 Days) | 9 |  |  | Avg. New Tasks Per Day (Last 30 Days) | 0 |  | 2019-12-22 | 0
|  | Avg. Completion (Last 7 Days) | 1.2857 |  |  | Expected Tasks (Next X Days) | 0 |  | 2019-12-21 | 0
|  | Tasks Completed (Last 30 Days) | 21 |  |  | Avg. Daily Completion Needed to Clear Backlog (in X Days) | 0
|  | Avg. Completion (Last 30 Days) | 0.7 |  |  | Remaining Tasks to Clear Backlog (in X Days) | 0 | Remaining Task Stretch Goal
|  | Tasks Completed (Last 365 Days) | 95 |  |  | New Effort (Last 30 Days) | 42
|  | Avg. Completion (Last 365 Days) | 0.26027 |  |  | Avg. New Effort Per Day (Last 30 Days) | 1.4
|  | Target Task Completion | 1.2857 |  |  | Expected Effort (Next X Days) | 42
|  | Effort (All Time) | 215 |  |  | Avg. Daily Effort Needed to Clear Backlog (in X Days) | 1.4
|  | Avg. Effort (All Time) | 0.32675 |  |  | Remaining Effort to Clear Backlog (in X Days) | 1.4
|  | Effort (Last 7 Days) | 18
|  | Avg. Effort (Last 7 Days) | 2.5714
|  | Effort (Last 30 Days) | 52
|  | Avg. Effort (Last 30 Days) | 1.7333
|  | Effort (Last 365 Days) | 196
|  | Avg. Effort (Last 365 Days) | 0.53699
|  | Target Effort Completion | 2.5714
|  | Tasks Completed Today | 0
|  | Effort Completed Today | 0
|  | Remaining Tasks Projected Today | 1.2857
|  | Remaining Tasks (adj for backlog max) | 0
|  | Remaining Tasks (adj for min 0) | 0
Remaining Tasks Overachiever
|  | Remaining Tasks with Stretch Goal | 0 | 0-0 Remaining Tasks Today
|  | Remaining Effort Projected Today | 2.5714
|  | Remaining Effort (adj for backlog max) | 0
|  | Remaining Effort (adj for min 0) | 0
Remaining Effort Overachiever
|  | Remaining Effort with Stretch Goal | 0 | 0-1 Remaining Effort
Formulas:
Quantity = MIN(tbTasks[Added On])
Quantity = MAX(tbTasks[Added On],tbTasks[Started On],tbTasks[Completed On])
Task Completion = [Task Completion, row above]-1
Count = COUNTIFS(tbTasks[Added On],">="&TODAY()-30)
Count = SUMIFS(tbTasks[Effort],tbTasks[Added On],">="&TODAY()-30)
0 Backlog Tasks
0-0 Remaining Tasks Today
0-1 Remaining Effort

## metricsProject (hidden)
Graph Ideas | Filters | User Input | Modified Input | Error Indicator | Result | Fix | Text Metric | Result | Text | Texbox | Overall By Status |  |  | Count by Category | [5 empty] | Count by Category by Status | [9 empty] | Tasks by Status Over Time |  |  |  |  | Callouts | Result | Textbox | Task Avg Days in Backlog and in Progress | [7 empty] | Selected Work vs. Other Work During Same Time Frame |  |  |  | Count Complete By Category Over Time
Count by Category | By Client |  | * |  |  |  | Start Date | 2018-03-04 08:58 | 2018-03-04 08:58 |  | Status | Count | Graph | Category | Refined Category | Count | Refined Categories | Counts | Graph | Category | Refined Category | Cnt Not Started | Cnt Started | Cnt Complete | Refined Categories | Not Started | Started | Complete | Graph | Date | Not Started | Started | Complete | Graph | Purpose (Client_Project) | #N/A |  | Category | Refined Category | Avg Time in Backlog | Avg Time in Progress | Refined Categories | Avg Time in Backlog | Avg Time in Progress | Graph | Date | Selected Work | Other Work | Graph | Category | Refined Category | 2019-12-31 | 2019-11-30 | 2019-10-31 | 2019-09-30 | 2019-08-31 | 2019-07-31 | 2019-06-30 | 2019-05-31 | 2019-04-30 | 2019-03-31 | 2019-02-28 | 2019-01-31 | 2018-12-31 | Project Utilized? | Refined Categories | 2019-12-31 | 2019-11-30 | 2019-10-31 | 2019-09-30 | 2019-08-31 | 2019-07-31 | 2019-06-30 | 2019-05-31 | 2019-04-30 | 2019-03-31 | 2019-02-28 | 2019-01-31 | 2018-12-31 | Graph
Count by Category by Status | By Project | ToDo | ToDo |  |  |  | End Date | 2019-12-20 | 2019-12-20 |  | Not Started | 0 |  | Access | Admin | 0 | Data | 2 |  | Access | Admin | 0 | 0 | 0 | Data | 0 | 0 | 2 |  | 2019-12-31 | 18 | 20 | 21 |  | Purpose(Project) | Enable superior tracking of all tasks, projects, and clients minimal continuous effort. |  | Access | Admin |  |  | Data | 1 | 1 |  | 2019-12-31 | 20 | 0 |  | Access | Potential Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Yes | Value Add | 19 | 1 | 3 | 5 | 8 | 25 | 9 | 1 | 1 | 0 | 0 | 11
Tasks by Status Over Time | By Stakeholders |  | * |  |  |  | Estimated Completion Date | 0 |  |  | Started | 0 |  | Admin | Admin | 9 | Fixes | 21 |  | Admin | Admin | 0 | 0 | 9 | Fixes | 0 | 0 | 21 |  | 2019-11-30 | 0 | 1 | 0 |  | Project Count | 1 |  | Admin | Admin | 17.5556 | 1.2222 | Fixes | 5.8855 | 1.0606 |  | 2019-11-30 | 1 | 0 |  | Admin | Potential Value Add | 1 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |  |  | Potential Value Add | 1 | 0 | 0 | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 0 | 1
Task Count by Category Over Time (100% area) | From Date |  | 1/1/1990 |  |  |  | % Complete | 100% | 100% Complete |  | Complete | 114 |  | Analysis | Data | 0 | Comm | 0 |  | Analysis | Data | 0 | 0 | 0 | Comm | 0 | 0 | 0 |  | 2019-10-31 | 2 | 3 | 3 |  | Purpose Callout | Purpose Enable superior tracking of all tasks, projects, and clients minimal continuous effort. |  | Analysis | Data |  |  | Comm | #DIV/0! | #DIV/0! |  | 2019-10-31 | 3 | 0 |  | Analysis | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Overall By Status | To Date |  | 12/31/2100 | [10 empty] | Bugs | Fixes | 1 | Setup | 8 |  | Bugs | Fixes | 0 | 0 | 1 | Setup | 0 | 0 | 8 |  | 2019-09-30 | 8 | 5 | 5 |  |  |  |  | Bugs | Fixes | 1 | 1 | Setup | 2.6 | 2.6667 |  | 2019-09-30 | 5 | 0 |  | Bugs | Value Add | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Start and End Dates | [13 empty] | Comm | Comm | 0 | Design | 20 |  | Comm | Comm | 0 | 0 | 0 | Design | 0 | 0 | 20 |  | 2019-08-31 | 11 | 14 | 14 |  |  |  |  | Comm | Comm |  |  | Design | 3 | 1 |  | 2019-08-31 | 14 | 0 |  | Comm | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimated Completion Date | [13 empty] | Core | Setup | 0 | Features | 44 |  | Core | Setup | 0 | 0 | 0 | Features | 0 | 0 | 44 |  | 2019-07-31 | 23 | 22 | 25 |  |  |  |  | Core | Setup |  |  | Features | 6.4091 | 2.25 |  | 2019-07-31 | 25 | 0 |  | Core | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Heat Map | [13 empty] | Data | Data | 2 | Admin | 15 |  | Data | Data | 0 | 0 | 2 | Admin | 0 | 0 | 15 |  | 2019-06-30 | 14 | 13 | 10 |  |  |  |  | Data | Data | 1 | 1 | Admin | 6.6019 | 1.2407 |  | 2019-06-30 | 10 | 0 |  | Data | Value Add | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
By Category Lists | [13 empty] | Design | Design | 0 | QA | 4 |  | Design | Design | 0 | 0 | 0 | QA | 0 | 0 | 4 |  | 2019-05-31 | 3 | 1 | 1 |  |  |  |  | Design | Design |  |  | QA | 3.75 | 1 |  | 2019-05-31 | 1 | 0 |  | Design | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Purpose Callout | [13 empty] | Discovery | Setup | 5 |  |  |  | Discovery | Setup | 0 | 0 | 5 | [5 empty] | 2019-04-30 | 1 | 1 | 1 |  |  |  |  | Discovery | Setup | 4.8 | 2 |  |  |  |  | 2019-04-30 | 1 | 0 |  | Discovery | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Avg. Time in Backlog vs. Time in Progress by Category | [13 empty] | Documentation | Setup | 2 |  |  |  | Documentation | Setup | 0 | 0 | 2 | [5 empty] | 2019-03-31 | 0 | 0 | 0 |  |  |  |  | Documentation | Setup | 1 | 1 |  |  |  |  | 2019-03-31 | 0 | 0 |  | Documentation | Value Add | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gantt Showing Selected Project vs. Other Projects | [13 empty] | Features | Features | 44 |  |  |  | Features | Features | 0 | 0 | 44 | [5 empty] | 2019-02-28 | 0 | 0 | 0 |  |  |  |  | Features | Features | 6.4091 | 2.25 |  |  |  |  | 2019-02-28 | 0 | 0 |  | Features | Value Add | 7 | 1 | 1 | 2 | 5 | 5 | 5 | 1 | 1 | 0 | 0 | 7
[14 empty] | Fixes | Fixes | 11 |  |  |  | Fixes | Fixes | 0 | 0 | 11 | [5 empty] | 2019-01-31 | 13 | 15 | 15 |  |  |  |  | Fixes | Fixes | 8.5455 | 1.1818 |  |  |  |  | 2019-01-31 | 15 | 0 |  | Fixes | Value Add | 2 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 3
[14 empty] | Goal | Setup | 1 |  |  |  | Goal | Setup | 0 | 0 | 1 | [5 empty] | 2018-12-31 | [7 empty] | Goal | Setup | 2 | 5 |  |  |  |  | 2018-12-31 | 0 | 0 |  | Goal | Value Add | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Impediment | Fixes | 0 |  |  |  | Impediment | Fixes | 0 | 0 | 0 | [13 empty] | Impediment | Fixes | [10 empty] | Impediment | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Maintenance | Admin | 0 |  |  |  | Maintenance | Admin | 0 | 0 | 0 | Admin | [12 empty] | Maintenance | Admin | [10 empty] | Maintenance | Potential Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Meeting | Comm | 0 |  |  |  | Meeting | Comm | 0 | 0 | 0 | Data | [12 empty] | Meeting | Comm | [10 empty] | Meeting | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Milestone | Setup | 0 |  |  |  | Milestone | Setup | 0 | 0 | 0 | Fixes | [12 empty] | Milestone | Setup | [10 empty] | Milestone | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Practice | Admin | 0 |  |  |  | Practice | Admin | 0 | 0 | 0 | Comm | [12 empty] | Practice | Admin | [10 empty] | Practice | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Prepare | Admin | 0 |  |  |  | Prepare | Admin | 0 | 0 | 0 | Setup | [12 empty] | Prepare | Admin | [10 empty] | Prepare | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | QA | QA | 4 |  |  |  | QA | QA | 0 | 0 | 4 | Design | [12 empty] | QA | QA | 3.75 | 1 | [8 empty] | QA | Value Add | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Refactoring | Fixes | 9 |  |  |  | Refactoring | Fixes | 0 | 0 | 9 | Features | [12 empty] | Refactoring | Fixes | 8.1111 | 1 | [8 empty] | Refactoring | Value Add | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Research | Setup | 0 |  |  |  | Research | Setup | 0 | 0 | 0 | QA | [12 empty] | Research | Setup | [10 empty] | Research | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Revise | Fixes | 0 |  |  |  | Revise | Fixes | 0 | 0 | 0 | [13 empty] | Revise | Fixes | [10 empty] | Revise | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Setup | Setup | 0 |  |  |  | Setup | Setup | 0 | 0 | 0 | [13 empty] | Setup | Setup | [10 empty] | Setup | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Study | Setup | 0 |  |  |  | Study | Setup | 0 | 0 | 0 | [13 empty] | Study | Setup | [10 empty] | Study | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Testing | QA | 0 |  |  |  | Testing | QA | 0 | 0 | 0 | [13 empty] | Testing | QA | [10 empty] | Testing | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Training | Setup | 0 |  |  |  | Training | Setup | 0 | 0 | 0 | [13 empty] | Training | Setup | [10 empty] | Training | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Updates | Admin | 2 |  |  |  | Updates | Admin | 0 | 0 | 2 | [13 empty] | Updates | Admin | 1 | 1 | [8 empty] | Updates | Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[14 empty] | Upkeep | Admin | 4 |  |  |  | Upkeep | Admin | 0 | 0 | 4 | [13 empty] | Upkeep | Admin | 1.25 | 1.5 | [8 empty] | Upkeep | Non-Value Add | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
[14 empty] | Visualization | Design | 20 |  |  |  | Visualization | Design | 0 | 0 | 20 | [13 empty] | Visualization | Design | 3 | 1 | [8 empty] | Visualization | Value Add | 0 | 0 | 0 | 1 | 1 | 14 | 4 | 0 | 0 | 0 | 0 | 0
Formulas:
Result = MINIFS(tbTasks[Started On], tbTasks[Client],E2, tbTasks[Project],E3, tbTasks[Added On],">="&E5, tbTasks[Added On],"<="&E6)
Result = MAXIFS(tbTasks[ETC], tbTasks[Client],E2, tbTasks[Project],E3, tbTasks[Added On],">="&E5, tbTasks[Added On],"<="&E6)
Text = [Result]
Tasks by Status Over Time = EOMONTH([Tasks by Status Over Time, row above],-1)
100% Complete
Purpose Enable superior tracking of all tasks, projects, and clients minimal continuous effort.
12/20/2019
3/4/2018